GENERAL DEPARTMENT OF VOCATIONAL TRAINING

DEPARTMENT OF VOCATIONAL TRAINING ACCREDITATION

-------------------------------

WORK PLAN IN VOCATIONAL QUALITY ACCREDITATION

FOR THE PERIOD 2009-2010 AND 2011-2020

I. FOR THE PERIOD 2009-2010

According to the Decision No. 541/QĐ-LĐTBXH dated 29/4/2009, the Minister of Labor, Invalids and Social Affairs approved the plan of implementing pilot vocational quality accreditation for the period 2009-2010. The main contents of this plan are as follows:

1. Objectives and requirements

1.1. Objectives

- Improve the legal system of vocational quality accreditation, organize assessing and directing the expansion of accreditation activities for vocational institutions in the following years.

- Develop policies of encouraging vocational institutions to take part in vocational accreditation activities.

- Strengthen the capacity for external evaluators and staffs of state – management offices in vocational quality accreditation.

1.2. Requirements

Vocational colleges, vocational secondary schools and vocational centres taking part in pilot vocational accreditation must meet the requirements of structures related to areas, governing offices and kinds of possession. Besides, the following requirements must be met (i) vocational colleges were established at least 3 years ago (for new establishments); vocational secondary schools and centers started to operate at least 2 years ago (for new establishments) (ii) vocational institutions must pledge to ensure the progress and requirements of vocational quality accreditation.

2. The scope and objectives of implementation

2.1. The scope:

The scope of implementing the pilot is in all 3 areas Northern Area, Middle Area and Southern Areas.

2.2. Objectives:

50 vocational colleges, vocational secondary schools and 10 vocational centers will be selected to take part in the pilot in the period 2009-2010. The selection must meet the requirements of structures related to areas, governing offices and kinds of possession.

3. Estimated results

- Organize training courses for 700 staffs that are in charge of self – evaluation in vocational institutions taking part in the pilot.

- Organize training courses for 200 external - evaluators.

- Implement the accreditation for 50 vocational colleges and secondary schools and 10 vocational centers: in 2009: 20 vocational colleges and secondary schools; in 2010: 30 vocational colleges and secondary schools and 10 vocational centers.

- Self – evaluation Reports of 50 vocational institutions taking part in the pilot.

- 01 Overview Report on vocational quality accreditation by the Consulting Firm.

- 01 Report on assessing the results of the pilot by General Department of Vocational Training.

- Decisions of the Minister on recognizing vocational institutions meeting the required vocational training accreditation.

- Proposals to adjust and supplement policies of vocational quality accreditation.

4. Activities

- Set up the plan of implementation and design the detailed estimation of expenditures.

- Organize surveys to select vocational institutions taking part in the pilot.

- Organize training courses for staffs who are in charge of self – evaluation in vocational institutions taking part in the pilot

-  Organize self – evaluation in vocational institutions taking part in the pilot.

- Organize comparative bidding to select the firm to implement the accreditation in vocational colleges and secondary schools taking part in the pilot.

- Implement the accreditation in selected vocational centres.

-  Organize training courses for external – evaluators.

- Appraise, recognize vocational institutions meeting  the required vocational training accreditation

- Organize a workshop on assessing vocational quality accreditation activities.

- Carry out propaganda compaigns on vocational institutions certified of quality accreditation.

5. Mode of implementation:

The pilot vocational quality accreditation for vocational colleges and secondary schools (in 2009 and 2010) is implemented by a consulting firm selected by comparative biddings. General Department of Vocational Training (GDVT) will estabilish teams of external – evaluators and be responsible for supervising the progress and quality of implementation.

Accreditaion for vocational centres (in 2010) will be implemented by the GDVT.

II. 	FOR THE PERIOD 2011-2020

The GDVT has developed the Draft “Project of Innovation and Development of Vocational Training to 2020” and is currently proceeding with procedures of submitting to the Government for approval. The work plan in the field of vocational quality accreditation to 2010 defined in this Draft is as follows:

- Objectives:

- For the period 2011 -2015

By the year 2015, 70% of vocational colleges and vocational secondary schools and 50% of vocational centers and training curriculums of  intermediate level, and advanced level will be accreditated.

- For the period 2016-2020

By the year 2020, 100% of vocational colleges and vocational secondary schools, vocational centers and  training curriculums of  intermediate level, and advanced level will be accreditated.

2. Methods of implementation

- Improve regulations on accreditation towards training institutions and training curriculum; issue policies of giving priorities to vocational institutions certified of quality accreditation.

- Speed up the accreditation of training curriculum of vocational institution.

- Select prestigious international organizations in the field of quality accreditation to implement accreditation in invested vocations to reach the regional and international standards.

- Organize training courses for external evaluators and staffs who are in charge of self – study of vocational institutions.

- Establish 03 public Centers of Vocational Accreditation in 3 areas (Northern Area, Middle Area, Southern Area) to train external evaluators self – study staffs, implement vocational accreditation, approve the establishment of private centers of vocational accreditation.

- Ministries, sectors and localities develop the plan and supervise vocational institutions under management in implementing self study and registering for vocational accreditation. The state will grant funds for external evaluation and self study of vocational institutions.

3. Implementation activities:

3.1. For the period 2011 -2015

- Develop regulations on Criteria and Standard Systems for accreditation of training curriculum and develop manuals for accreditation of training curriculum.

- Train 3,000 self –study staffs of vocational colleges and vocational secondary schools.

- Train 1,500 self – study staffs of vocational centers.

- Train 200 self – study staffs in curriculum accreditation

- Train 30 external - evaluators in foreign countries

- Train 500 external – evaluators

- Support the self – study for 200 vocational colleges and vocational secondary schools.

- Implement the accreditation of 200 vocational colleges and vocational secondary schools.

- Support the self – study for 200 vocational centers.

- Implement the accreditation of 200 vocational centers

- Implement the accreditation of 500 training curriculum

3.2. For the period 2016 -2020

- Adjust, supplement and improve Criteria and Standard Systems for accreditation and manuals of accreditation.

- Train 3,600 self –study staffs of vocational colleges and vocational secondary schools

- Train 3,500 self –study staffs of vocational centers.

- Train 200 self – study staffs of training curriculum accreditation.

- Train 500 external – evaluators.

- Support the self – study for 150 vocational colleges and secondary schools.

-  Implement the accreditation 210 vocational colleges and secondary schools

- Support the self – study for 500 vocational centers.

- Implement the accreditation of 600 vocational centers

-  Implement the accreditation of 200 training curriculum

FOR THE DIRECTOR

DEPUTY DIRECTOR

Pham Vu Quoc Binh